## Instructions
PROJECT COSTING WORKBOOK
BayOne Solutions — Outcome-Based Engagement Pricing
PURPOSE
This workbook models the internal cost of delivering an outcome-based consulting engagement. It helps you determine whether a quoted price supports your target margin at a given team structure and timeline. It models two delivery scenarios (shorter vs. longer timeline) and a discount sensitivity analysis for the longer-timeline option.
HOW TO USE
1. Start on the INPUTS tab. Fill in your project details, personnel rates, and scenario parameters. 2. The SCENARIO A and SCENARIO B tabs auto-calculate based on your inputs. 3. Use the DISCOUNT ANALYSIS tab to see how much room you have to negotiate on price. 4. The COMPARISON tab gives you a side-by-side view of all scenarios. 5. The THROUGHPUT tab validates whether your team can actually deliver the scope in the timeline.
KEY CONCEPTS
Allocation % This is a COST ALLOCATION mechanism, not a productivity measure. If a person is 50% allocated, it means 50% of their cost is charged to this project. The other 50% is charged elsewhere. The person still works full-time. Allocation splits cost across projects.
Rate Type (Annual vs. Hourly) Each resource is either salaried (Annual) or contracted (Hourly). This determines how the Loaded Monthly cost is calculated: - Annual: Loaded Annual / 12 - Hourly: Loaded Hourly × Working Hours per Month
Risk Reserve A percentage buffer added on top of base cost to account for scope creep, technical complexity, and unknowns. This is not a guaranteed spend. It sits inside the gross margin as protection. If nothing goes wrong, the risk reserve becomes additional margin.
Stabilization & Acceptance The final phase of each scenario. This is NOT a separate QA phase. Development is agile and testing happens throughout. This buffer covers production-level validation after client integration, bug fixes, stakeholder demos, and final acceptance.
Base Cost vs. Loaded Cost - Base Cost = Personnel + Travel + Hardware/Consumables (what you expect to spend) - Loaded Cost = Base Cost + Risk Reserve (worst-case budget) - Margin on Base = best case (if risk doesn't materialize) - Margin on Loaded = worst case (if full risk reserve is consumed)
EDITABLE FIELDS
Cells with a LIGHT YELLOW background are user-editable inputs. All other cells contain formulas. Do not overwrite formula cells.
ADDING RESOURCES
To add a new resource, insert a row in the Personnel Rates table on the Inputs tab. Set the Rate Type to Annual or Hourly. The formulas will handle the rest. Then add a corresponding row on each Scenario tab.
SAMPLE DATA
This workbook ships with sample data for a fictional engagement. Clear the sample data on the Inputs tab and replace with your project details. All scenario tabs will update automatically.

## Inputs
Project Details
Project Name | Acme Corp Platform Migration
Client | Acme Corporation
Engagement Type | Legacy Platform Conversion
Deliverable | 120 screens, full-stack (UI + backend)
Pricing Model | Outcome-based, fixed price
Personnel Rates
Resource | Rate Type | Base Rate | Load Factor | Loaded Rate | Loaded Monthly | Allocation % | Effective Monthly
Project Lead | Annual | 150000 | 1.2 | 180000 | 15000 | 25% | 3750
Senior Engineer (US) | Annual | 120000 | 1.2 | 144000 | 12000 | 100% | 12000
Offshore Engineer 1 | Hourly | 30 | 1.2 | 36 | 6239.88 | 100% | 6239.88
Offshore Engineer 2 | Hourly | 25 | 1.2 | 30 | 5199.9 | 100% | 5199.9
Offshore Engineer 3 | Hourly | 28 | 1.2 | 33.6 | 5823.888 | 100% | 5823.888
Constants
Load Factor (default) | 1.2
Working Hours per Month | 173.33
Engagement Parameters
Revenue | 350000
Total Deliverable Units (screens, modules, etc.) | 120
Hours per Unit (estimated, with tooling) | 10
Total Delivery Hours | 1200
Risk Reserve % | 25%
POC Duration (months) | 1
POC Resource | Project Lead
POC Hours | 60
POC Cost (absorbed) | 5192.3077
Travel & Expenses
Cost per Trip | 2500
Trips (Scenario A) | 2
Trips (Scenario B) | 3
Travel Destination | Client HQ
Hardware & Consumables
Monthly Tools & Subscriptions | 0
One-Time Equipment | 0
Margin Thresholds
Scenario A Target (ideal) | 40%
Scenario A Floor | 40%
Scenario B Target (ideal) | 40%
Scenario B Floor (minimum acceptable) | 30%
Scenario Parameters
Scenario Label | Q3 Delivery | Q4 Delivery
Offshore Engineers (dev phase) | 5 | 2
Offshore Engineers (stabilization) | 4 | 2
Dev Months (post-POC) | 2 | 5
Stabilization & Acceptance Months | 1 | 2
Total Post-POC Months | 3 | 7
Note on B20: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Standard: 173.33 (52w × 40h / 12). Adjust to 160-168 for realistic availability after holidays/PTO.

## Scenario A
Scenario A: Q3 Delivery — Accelerated Delivery (More Resources, Shorter Timeline)
POC (1 month) + 2 dev months + 1 stabilization month(s) = 4 months total
Resource | Month 1 (POC) | Month 2 | Month 3 | Month 4 (Stab.) | Total
Project Lead | 5192.3077 | 3750 | 3750 | 3750 | 16442.3077
Senior Engineer (US) | 0 | 12000 | 12000 | 12000 | 36000
Offshore Engineers (dev) | 0 | 28772.78 | 28772.78 | 0 | 57545.56
Offshore Engineers (stab.) | 0 | 0 | 0 | 23018.224 | 23018.224
Personnel Total | 5192.3077 | 44522.78 | 44522.78 | 38768.224 | 133006.0917
Cumulative | 5192.3077 | 49715.0877 | 94237.8677 | 133006.0917
Financial Summary
Revenue | 350000
Personnel Cost | 133006.0917
Travel & Expenses | 5000
Hardware & Consumables | 0
Base Cost | 138006.0917
Risk Reserve | 34501.5229
Loaded Cost | 172507.6146
Margin on Loaded Cost ($) | 177492.3854
Margin on Loaded Cost (%) | 50.71%
Margin on Base Cost ($) | 211993.9083
Margin on Base Cost (%) | 60.57%
Above Floor? (loaded) | YES
Above Floor? (base) | YES
Per-Unit Economics
Cost per Unit (base) | 1150.0508
Cost per Unit (loaded) | 1437.5635
Revenue per Unit | 2916.6667
Margin per Unit | 1479.1032
Staffing Summary
Total Duration (months) | 4
Peak Headcount | 7
Peak Monthly Burn | 44522.78
Avg Monthly Burn | 33251.5229

## Scenario B
Scenario B: Q4 Delivery — Extended Timeline (Fewer Resources, Longer Duration)
POC (1 month) + 5 dev months + 2 stabilization months = 8 months total
Resource | Month 1 (POC) | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 7 (Stab.) | Month 8 (Stab.) | Total
Project Lead | 5192.3077 | 3750 | 3750 | 3750 | 3750 | 3750 | 3750 | 3750 | 31442.3077
Senior Engineer (US) | 0 | 12000 | 12000 | 12000 | 12000 | 12000 | 6000 | 6000 | 72000
Offshore Engineers (dev) | 0 | 11509.112 | 11509.112 | 11509.112 | 11509.112 | 11509.112 | 0 | 0 | 57545.56
Offshore Engineers (stab.) | 0 | 0 | 0 | 0 | 0 | 0 | 11509.112 | 11509.112 | 23018.224
Personnel Total | 5192.3077 | 27259.112 | 27259.112 | 27259.112 | 27259.112 | 27259.112 | 21259.112 | 21259.112 | 184006.0917
Cumulative | 5192.3077 | 32451.4197 | 59710.5317 | 86969.6437 | 114228.7557 | 141487.8677 | 162746.9797 | 184006.0917
Financial Summary
Revenue | 350000
Personnel Cost | 184006.0917
Travel & Expenses | 7500
Hardware & Consumables | 0
Base Cost | 191506.0917
Risk Reserve | 47876.5229
Loaded Cost | 239382.6146
Margin on Loaded Cost ($) | 110617.3854
Margin on Loaded Cost (%) | 31.6%
Margin on Base Cost ($) | 158493.9083
Margin on Base Cost (%) | 45.28%
Above Floor? (loaded) | YES
Above Floor? (base) | YES
Per-Unit Economics
Cost per Unit (base) | 1595.8841
Cost per Unit (loaded) | 1994.8551
Revenue per Unit | 2916.6667
Margin per Unit | 921.8115
Staffing Summary
Total Duration (months) | 8
Peak Headcount | 4
Peak Monthly Burn | 27259.112
Avg Monthly Burn | 23000.7615

## Discount Analysis
Discount Sensitivity — Scenario B Timeline Only
Base Cost (from Scenario B): | 191506.0917
Loaded Cost (from Scenario B): | 239382.6146
Price | Discount % | Margin $ (loaded) | Margin % (loaded) | Margin $ (base) | Margin % (base) | Verdict
350000 | 0% | 110617.3854 | 31.6% | 158493.9083 | 45.28% | SAFE
332500 | 5% | 93117.3854 | 28.01% | 140993.9083 | 42.4% | BELOW FLOOR
315000 | 10% | 75617.3854 | 24.01% | 123493.9083 | 39.2% | BELOW FLOOR
297500 | 15% | 58117.3854 | 19.54% | 105993.9083 | 35.63% | BELOW FLOOR
280000 | 20% | 40617.3854 | 14.51% | 88493.9083 | 31.6% | BELOW FLOOR
262500 | 25% | 23117.3854 | 8.807% | 70993.9083 | 27.05% | BELOW FLOOR
245000 | 30% | 5617.3854 | 2.293% | 53493.9083 | 21.83% | BELOW FLOOR
Floor Prices
Floor at margin target (loaded) | 341975.1637
Max discount % (loaded) | 2.293%
Floor at margin target (base) | 273580.131
Max discount % (base) | 21.83%

## Comparison
Scenario Comparison Dashboard
Metric | Scenario A | Scenario B | Discount (floor)
Revenue | 350000 | 350000 | 341975.1637
Base Cost | 138006.0917 | 191506.0917 | 191506.0917
Risk Reserve | 34501.5229 | 47876.5229 | 47876.5229
Loaded Cost | 172507.6146 | 239382.6146 | 239382.6146
Margin % (loaded) | 50.71% | 31.6% | 30%
Margin % (base) | 60.57% | 45.28% | 44%
Duration (months) | 4 | 8 | 8
Peak Headcount | 7 | 4 | 4
Cost per Unit (loaded) | 1437.5635 | 1994.8551 | 1994.8551
Revenue per Unit | 2916.6667 | 2916.6667 | 2849.793
Avg Monthly Burn | 33251.5229 | 23000.7615 | 23000.7615
Above Floor? (loaded) | YES | YES | YES

## Throughput
Delivery Throughput Validation
Delivery Requirements
Total Deliverable Units | 120
Hours per Unit | 10
Total Hours Needed | 1200
Scenario A Capacity
Offshore Engineers (dev phase) | 5
Hours per Month per Engineer | 173.33
Dev Months | 2
Total Available Dev Hours | 1733.3
Units Possible | 173.33
Utilization % | 69.23%
Scenario B Capacity
Offshore Engineers (dev phase) | 2
Hours per Month per Engineer | 173.33
Dev Months | 5
Total Available Dev Hours | 1733.3
Units Possible | 173.33
Utilization % | 69.23%